## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-1 | Set up the complete project environment by installing and configuring the JDK, creating and linking the GitHub repository, and initializing the development workspace using GitHub Codespaces. Ensure all dependencies and tools are properly configured for smooth project execution. | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 1 | Sprint 1 | US-2 | Design and implement the Product model class to define product attributes and behaviors. Develop the InventoryManager class using Object-Oriented Programming principles to handle core inventory operations such as adding, updating, searching, and deleting products efficiently. | MUST HAVE | US-1 | Divyansh Shrivastava | 3- Completed
Sprint 1 | Sprint 1 | US-3 | Use Git and GitHub to manage project versions, commit changes, and push code for collaboration. | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 1 | Sprint 1 | US-4 | Practice basic SQL commands like creating tables, inserting, updating, and retrieving data. Test the JDBC connection to ensure the Java application can successfully connect and interact with the database. | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 2 | Sprint 2 | US-5 | Implement read operations such as fetching all products and retrieving a product by its ID. Integrate these functions into the console menu to allow users to view product details directly from the command-line interface | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 2 | Sprint 2 | US-6 | Implement centralized exception handling to manage runtime errors gracefully. Ensure meaningful error messages are displayed and system stability is maintained during unexpected failures | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 2 | Sprint 2 | US-7 | Integrate all CRUD operations (Create, Read, Update, Delete) into the console menu. Perform end-to-end testing to ensure each operation works correctly and interacts smoothly with the database and user interface. | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 2 | Sprint 2 | US-8 | Enhance the search functionality by adding options to search products by ID, name, category, and price range. Ensure accurate filtering and display of results in the console menu for better usability. | SHOULD HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 2 | Sprint 2 | US-9 | Implement input validation to ensure correct data entry and add error handling to manage invalid inputs or system exceptions gracefully, improving overall reliability and user experience. | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 2 | Sprint 2 | US-10 | Implement JUnit test cases to verify the functionality of core modules. Ensure all methods are properly tested for accuracy, reliability, and error handling. | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 3 | Sprint 3 | US-11 | Implement a user registration and login system to manage authenticated access. Store user credentials securely and verify login details to ensure only authorized users can access the application | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 3 | Sprint 3 | US-12 | Implement a CSVHelper utility to export inventory data into CSV files. Ensure the exported files include all relevant product details and can be easily shared or analyzed | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 3 | Sprint 3 | US-13 | Implement role-based access control by segregating inventory options for Admin and User roles. Grant Admins full system access, while restricting regular Users to limited functionalities such as viewing and searching inventory data | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 3 | Sprint 3 | US-14 | Add a “Generate Report” option in the Admin Menu to allow administrators to create and view inventory reports. Enable report generation in preferred formats such as CSV for easy analysis and record-keeping. | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 3 | Sprint 3 | US-15 | Develop an EmailService using the JavaMail API to send inventory reports via SMTP. Configure sender credentials, compose email messages, and ensure successful delivery of reports to specified recipients. | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 3 | Sprint 3 | US-16 | Integrate the Database, CSV, and Email modules to enable complete automated reporting. Ensure data is fetched from the database, exported to a CSV file, and sent via email seamlessly as part of the reporting workflow. | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 3 | Sprint 3 | US-17 | Update the registration system to include an email input field. Store the user’s email during signup so it can be used later for verification or communication purposes. | SHOULD HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 3 | Sprint 3 | US-18 | Add a “Verify Email” option in the main menu for OTP verification. Generate and send a one-time password to the user’s email, then validate the entered OTP to confirm and verify the email address | COULD HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 4 | Sprint 4 | US-19 | Implement stock monitoring logic to automatically detect and flag low-stock products. It will check quantities of product fall below a defined threshold to help maintain optimal inventory levels. | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 4 | Sprint 4 | US-20 | Develop and schedule an automated stock alert generator that periodically checks inventory levels. Configure it to send alerts for low-stock items at scheduled intervals, ensuring timely restocking and continuous monitoring | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 4 | Sprint 4 | US-21 | Integrate an email notification system to automatically inform users about low-stock products. Configure the system to send detailed alerts with product information whenever inventory levels drop below the defined threshold. | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Sprint 4 | Sprint 4 | US-22 | Build the project into a JAR file and deploy it to the cloud. Test the deployment to ensure the application runs smoothly in the hosted environment | MUST HAVE |  | Divyansh Shrivastava | 3- Completed
Note on F1: ====== ID#AAABqnR-1bo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.